## Traceability Matrix
Requirement ID | Requirement Description | UC1 | UC2 | UC3 | UC4 | UC5 | Check
1.1 | Automated attendance tracking for university lecturers | / |  |  |  |  | /
1.2 | Support multiple registered devices (smartphones, tablets, computers) | / |  |  |  |  | /
1.3 | Restrict attendance recording to registered devices |  | / |  |  |  | /
1.4 | Store attendance records in a cloud-hosted MySQL database |  | / | / |  |  | /
1.5 | Provide REST API endpoints for data access and modification |  |  | / |  | / | /
2.1.1 | Lecturers can register devices, record attendance, manage students, and generate reports | / | / |  |  |  | /
2.1.2 | Administrators can manage lecturers, students, courses, and attendance records |  | / | / |  |  | /
2.1.3 | Students are identified in the system and associated with attendance records |  | / |  | / |  | /
2.2 | Only registered devices can record attendance |  | / |  |  |  | /
2.3 | Persist user-related data (lecturers, students, courses) |  | / | / |  |  | /
3.1 | Lecturers can record attendance using a registered device | / |  |  |  |  | /
3.2 | Attendance records are stored in a database |  | / | / |  |  | /
3.3 | Prevent unauthorized devices from recording attendance |  | / |  |  |  | /
3.4 | Generate attendance reports |  |  | / | / |  | /
4.1 | Lecturers can register one or more devices | / | / |  | / |  | /
4.1 | Functionality to locate a registered device |  | / |  |  |  | /
5.1 | Store student profiles (name, university ID) |  | / |  |  |  | /
5.2 | Capture and store passport-style photos for students |  | / |  |  |  | /
6.1 | Store and manage courses |  | / |  | / |  | /
6.2 | Associate students with courses |  | / |  | / |  | /
6.3 | Associate lecturers with courses |  | / |  | / |  | /
7.1.1 | Generate attendance records reports |  |  | / |  |  | /
7.1.2 | Generate student lists |  |  | / |  |  | /
7.1.3 | Generate lecturer lists |  |  | / |  |  | /
7.1.4 | Generate course lists |  |  | / |  |  | /
7.1.5 | Generate student enrollments in courses |  |  | / |  |  | /
7.2.1 | Support adding new records |  |  | / |  |  | /
7.2.2 | Support modifying records |  |  | / |  |  | /
7.2.3 | Support deleting records |  |  | / |  |  | /
7.2.4 | Support viewing records |  |  | / |  | / | /
8.1 | Use a cloud-hosted MySQL database |  | / | / |  |  | /
8.2 | Provide database access via a REST API |  |  | / |  | / | /
9.1.1 | Conduct User Acceptance Testing (UAT) |  |  |  | / | / | /
9.1.2 | Conduct System Testing |  |  |  | / |  | /
9.1.3 | Conduct Unit Testing (where applicable) |  |  |  | / |  | /

## Project Plan
PROJECT X - AUTOMATED ATTENDANCE SYSTEM
Deadline: May 02, 2025 | [5 empty] | Days Left: 36 Days |  |  |  | Task Done:
Start date - March 1, 2025 |  | End date - May 2, 2025 |  | Actual Start Date - 03/21/2025 |  |  |  | Actual End Date - 05/02/2025
Task ID | Task Name | Sub Task ID | Sub Task Name | Deliverables | Assigned To: | Estimated Hours (Days) | Plan Start Date | Actual Start Date | Plan End Date | Actual End Date | Status
1 | Project Initiation | 1.1 | Define project objectives | Project scope document | GILLIENE JIMENEZ | 1 | 2025-03-21 | 03-21-2025 |  | 03-21-2025 | Done
|  | 1.2 | Project closure & documentation | Stakeholder list | RALPH CANONIGO | 1 | 2025-03-22 | 03-22-2025 |  | 03-22-2025 | Done
|  | 1.3 | Conduct feasibility study | Feasibility report | JOHN MAIZ | 1 | 2025-03-23 | 03-23-2025 |  | 03-23-2025 | Done
|  | 1.4 | Create project plan | Project plan document | GILLIENE JIMENEZ | 1 | 2025-03-24 | 03-24-2025 |  | 03-24-2025 | Done
|  | 1.5 | Obtain approvals | Approved project charter | CAPSTONERS | 1 | 2025-03-25 | 03-25-2025 |  | 03-25-2025 | Done
2 | Requirement Analysis | 2.1 | Gather functional requirements | Requirement specification document | MAIZ & CANONIGO | 1 | 2025-03-26 | 03-26-2025 |  | 03-26-2025 | Done
|  | 2.2 | Gather non-functional requirements | Performance & security requirements | GILLIENE JIMENEZ | 1 | 2025-03-27 | 03-27-2025 |  | 03-27-2025 | Done
|  | 2.3 | Define system architecture | System architecture diagram |  | 2 | 2025-03-28 | 03-28-2025 |  | 03-29-2025 | Pending
|  | 2.4 | Create wireframes/mockups | UI wireframes |  | 2 | 2025-03-30 | 03-30-2025 |  | 03-31-2025 | Pending
3 | Design Phase | 3.1 | Database design | ERD and database schema |  | 3 | 2025-04-01 | 2025-01-04 |  | 2025-03-04 | Pending
|  | 3.2 | API design | API documentation |  | 2 | 2025-04-04 | 2025-04-04 |  | 2025-05-04 | Pending
|  | 3.3 | UI/UX design | Final UI/UX designs |  | 2 | 2025-04-06 | 2025-06-04 |  | 2025-07-04 | Pending
|  | 3.4 | Security design | Security measures document |  | 4 | 2025-04-08 | 2025-08-04 |  | 2025-11-04 | Pending
4 | Development Phase | 4.1 | Set up development environment | Configured development tools |  | 1 | 2025-04-12 | 2025-12-04 |  | 2025-12-04 | Pending
|  | 4.2 | Frontend development (React Native) | Initial UI screens |  | 3 | 2025-04-13 | 04-13-2025 |  | 04-15-2025 | Pending
|  | 4.3 | Backend development | Working backend APIs |  | 5 | 2025-04-16 | 04-16-2025 |  | 04-20-2025 | Pending
|  | 4.4 | QR Code scanning implementation | Functional QR scanner module |  | 2 | 2025-04-21 | 04-21-2025 |  | 04-22-2025 | Pending
|  | 4.5 | GPS validation implementation | Functional GPS validation |  | 3 | 2025-04-23 | 04-23-2025 |  | 04-25-2025 | Pending
|  | 4.6 | Secure storage implementation | Encrypted storage module |  | 2 | 2025-04-26 | 04-26-2025 |  | 04-27-2025 | Pending
|  | 4.7 | Testing unit integration | Test reports |  | 1 | 2025-04-28 | 04-28-2025 |  | 04-28-2025 | Pending
5 | Testing & QA | 5.1 | Functional testing | Test case reports |  | 1 | 2025-04-29 | 04-29-2025 |  | 04-29-2025 | Pending
|  | 5.2 | Security testing | Security vulnerability report |  | 1 | 2025-04-30 | 04-30-2025 |  | 04-30-2025 | Pending
|  | 5.3 | User acceptance testing | User feedback & approval |  | 1 | 2025-05-01 | 2025-01-05 |  | 2025-01-05 | Pending
6 | Deployment | 6.1 | Prepare deployment environment | Deployment guide |  | 1 | 2025-05-02 | 2025-02-05 |  | 2025-02-05 | Pending
|  | 6.2 | Deploy backend API | Hosted backend |  | 2 | 2025-05-03 | 2025-03-05 |  | 2025-04-05 | Pending
|  | 6.3 | Deploy mobile app (beta) | Beta version released |  | 1 | 2025-05-05 | 2025-05-05 |  | 2025-05-05 | Pending
|  | 6.4 | Fix deployment issues | Issue resolution report |  | 3 | 2025-05-06 | 2025-06-05 |  | 2025-08-05 | Pending
|  | 6.5 | Release final version | Live mobile app |  | 1 | 2025-05-09 | 2025-09-05 |  | 2025-09-05 | Pending
7 | Final Demonstration | 7.1 | Prepare presentation materials | Presentation slides |  | 1 | 2025-05-10 | 2025-10-05 |  | 2025-10-05 | Pending
|  | 7.2 | Conduct demo for stakeholders | Live demonstration |  | 1 | 2025-05-11 | 2025-11-05 |  | 2025-11-05 | Pending
|  | 7.3 | Gather final feedback | Feedback report |  | 1 | 2025-05-12 | 2025-12-05 |  | 2025-12-05 | Pending
|  | 7.4 | Project closure & documentation | Final project report |  | 1 | 2025-05-13 | 05-13-2025 |  | 05-13-2025 | Pending
Formulas:
Plan Start Date = [Plan Start Date, row above]+[Days Left: 36 Days, row above]